## WBS-Work Plan
TASK | Start Date | End Date | Workdays (or hours) | Responsibility | Deliverable | Comments
Organize Team and Conduct Intial Team Meeting | 2023-01-27 | 2023-01-30 |  | UIC Team
Draft Project Plan and Statement of Work | 2023-01-31 | 2023-02-03 |  | UIC Team | Draft Project Plan and Statement of Work
Initial Sponsor Meeting | 2023-02-06 | 2023-02-06 |  | Client + UICTeam
Finalize Project Plan & Statement of Work | 2023-02-06 | 2023-02-10 |  | Client + UICTeam | Project Plan and Statement of Work
Requirements Definition | 2023-02-06 | 2023-02-17 |  | UIC Team | Technical Design Document
Design | 2023-02-20 | 2023-03-03 |  | UIC Team | Technical Design Document
Development | 2023-03-06 | 2023-03-17 |  | UIC Team
Testing | 2023-03-27 | 2023-04-07 |  | UIC Team | Unit Test Cases and Results
Implementation/Rollout | 2023-04-10 | 2023-04-21 |  | UIC Team | Source Codes
Prepare Final Presentation/Report and Package Final Deliverables for Project Sponsor | 2023-04-17 | 2023-05-05 |  | Client + UICTeam | Demo of the App to client, Final Report

## Gantt Chart (2)
Week Of
TASK | % Compl. | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01
Organize Team and Conduct Intial Team Meeting | 100%
Draft Project Plan and Statement of Work | 100%
Initial Sponsor Meeting | 100%
Finalize Project Plan & Statement of Work | 100%
Requirements Definition | 100%
Design | 100%
Training and Certifications | 100%
Development | 100%
Testing | 100%
Implementation/Rollout | 100%
Prepare Final Presentation/Report and Package Final Deliverables for Project Sponsor | 100%